## Table 1
Timeline to Develop and Submit College of Health Professions Grant Applications
PI Name: |  | Cayuse #: | FOA #:
Initiation | Date | Planning | Timeline (based on sponsor due date) | Management and Execution of Tasks | Date received notice of intent to submit | Date of Project Kickoff Meeting | Requested draft budget (25 day advance request) | work days | Requested Budget (20 day advance request) | work days | Deadline to CoHP (10 day advance request) | work days | SubAward | Deadline to submit final documents (9 business day advance request) | work days | Deadline to OSP (7 business days) | Work days | Sponsor Deadline
Application Development Phase
Milestone 1 |  | Kickoff meeting | 6 Weeks | Project kick-off meeting with CoHP Pre-Award Team; Develop timeline, discuss specific project guidelines and requirements; Identify key and other personnel and possible subaward collaborators and project roles; identify any additional assistance needed, ie, techical writing | 2023-08-24 | TBS | 2023-09-05 | -25 | 2023-09-12 | -20 | 2023-09-26 | -10 | N | 2023-10-05 | -9 | 2023-10-09 | -7 | 2023-10-17
Milestone 2 |  | Develop budget and administrative documents | 5 Weeks | Work with Pre-Award to develop budget and justification; Biosketches for all key personnel and consultants; Request Letters of Support; Data Management Plan, etc.
Milestone 3 |  | Subaward (if applicable) | 5 weeks | Pre-Award Team will work with PI and Subreceipent to gather all required subaward documents (budget and justification, biosketch, SOW, subreceipent commitment agreement)
Milestone 4 |  | Follow-Up Meeting (Tenative) | 3 weeks | Follow-up meeting (PI and Pre-Award Team) to review progress
Milestone 5 |  | Finalize Subaward (if applicable) | 3 weeks | Deadline to receive subreceipent subaward documents
Milestone 6 |  | Finalize Budget and Administrative Documents | 3 Weeks | Finalize budget and justification and all required non-science documents for CoHP Pre-Award Team (Resources, Equipment, Biosketches, Letters of Support, Budget Justification, Multiple PI Leadership Plan, Data Management Plan, etc.); Pre-Award will review formatting, compliance, etc.
Final Application Preparation and Submission Phase
Milestone 7 |  | Budget and Justification review by CoHP finance | 14 business days | Pre-Award Team will forward FINAL budget and budget justification to CoHP Finance for final review and approval (including subward documents, if applicable)
Milestone 8 |  | Presubmission Meeting | 10 business days | Presubmission meeting (PI and Pre-Award Team) to finalize application and prepare for submission
Milestone 9 |  | Finalize ALL Documents | 9 Business Days | Finalize science-related applicable documents (Project Narrative, Project Summary/Abstract, Project Narrative (lay abstract), Human Subjects, Enrollment Table, Vertebrate Animals, Authentication of Key Resources, etc.); save all documents in share file (one-drive); CoHP Pre-Award Team will review proposal for missing components, documents and compliance requirements; and perform final format review, etc; Prepare application for submission to Office of Sponsored Programs
Milestone 10 |  | Route application to OSP | 7 Business Days from sponsor due date | Route final Cayuse application for department and institutional review and approval.
Milestone 11 |  | Submit application to Sponsor (OSP) | 2 Business Days from sponsor due date | Office Sponsored Programs submits final application to sponsor.
Rev: 11/29/2023
2023 Holidays
2023-01-02
2023-01-16
2023-04-07
2023-05-29
2023-06-19
2023-07-04
2023-09-04
2023-11-23
2023-11-24
2023-12-25
2023-12-26
2023-12-27
2023-12-28
2023-12-29
Formulas:
Deadline to OSP (7 business days) = WORKDAY([Sponsor Deadline]+1, [Work days],M20:M33)